## Test Plan
OPENCART MANUAL TESTING (TEST PLAN )
PROJECT NAME | OPENCART E-COMMERCE APPLICATION ( MANUAL TESTING)
APPLICATION URL | https://www.opencart.com/ (LOCAL INSTALLATION)
DOCUMENTATION VERSION | V 1.0
PREPARED BY | KRISHNA SINGH
DATE | 2026-05-26
REVIEWED BY | [LEAD/MENTOR NAME]
OBJECTIVE
PURPOSE | To validate the functional behaviour of the OpenCart e-commerce demo application through structured manual testing covering all major modules.
GOAL | Ensure the application works correctly, identify defects, and report them in a structured format.
SCOPE MODULE UNDER TEST
INCLUDED | User Registration & Login ¦ Product Search & Browsing ¦ Shopping Cart ¦ Checkout Process ¦ My Account ¦ Wish List ¦ Product Review ¦ Forgot Password ¦ Header & Footer Navigation
EXCLUDED | Payment Gateway (live transactions) ¦ Admin Panel ¦ Performance / Load Testing ¦ API Testing
TEST APPROACH
TYPE | Black-Box Manual Functional Testing
TECHNIQUE | Equivalence Partitioning ¦ Boundary Value Analysis ¦ Exploratory Testing ¦ Error Guessing
ENTRY CRITERIA | Application is accessible ¦ Test data prepared ¦ Test cases reviewed
EXIT CRITERIA | All High & Medium priority test cases executed ¦ All Critical/High bugs reported ¦ Test summary report prepared
TEST ENVIRONMENT
BROWSER | Chrome (Google) Latest
OS | Window 10/11
URL | https://www.opencart.com
TEST DATA | Valid user: test@example.com / Test@123 ¦ Invalid data sets prepared per test case
ROLES AND RESPONSIBILITIES
TESTER | Krishna Singh - Write Test Case And Execute Test Case ,Log Bugs
TESTER LEAD | [Mentor Name] - Review the test case & Bug Report
DEFECT SEVERITY CLASSIFICATION
CRITICAL (S1) | Application crash, data loss, login failure – blocks all testing
HIGH(S2) | Major feature broken – significant business impact
MEDIUM(S3) | Feature works with workaround – moderate impact
LOW(S4) | Minor UI issues, typos – minimal impact

## Test Case
Test Case
TC ID | Module | Sub-Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC_REG_001 | User Registration | Register | Verify successful registration with valid data | 1. Go to Register page 2. Enter all mandatory fields with valid data 3. Click Continue | Fname: John ¦ Lname: Doe Email:- ks679485@gmail.com Pass: Test@123 | User registered successfully. Redirected to 'Your Account Has Been Created' page. | Registered successfully user redirected to 'Your Account Has Been Created' page | Pass | High
TC_REG_002 | User Registration | Register | Verify registration with already registered email | 1. Go to Register page 2. Enter an already used email 3. Fill other fields 4. Click Continue | Email: ks679485@gmail.com | Error message: 'E-Mail Address is already registered!' | Message Showed Error: E-Mail Address is already registered! | Pass | High
TC_REG_003 | User Registration | Register | Verify registration with blank mandatory fields | 1. Go to Register page 2. Leave all fields blank 3. Click Continue | All fields blank | Validation errors displayed for each mandatory field. | errors displayed for each mandatory field | Pass | High
TC_REG_004 | User Registration | Register | Verify invalid email format is rejected | 1. Go to Register page 2. Enter invalid email (abc@) 3. Fill other fields 4. Click Continue | Email: abc@ | Validation error: Invalid email format. | Validation error:- E-Mail Address does not appear to be valid! | Pass | Medium
TC_REG_005 | User Registration | Register | Verify password less than 4 characters is rejected | 1. Go to Register page 2. Fill other fields 3. Enter password with 3 characters 4. Click Continue | Password: Abc | Validation: 'Password must be between 4 and 20 characters!' | Validation error:- Password must be between 4 and 20 characters! | Pass | Medium
TC_LOG_001 | Login | Login Page | Verify login with valid credentials | 1. Navigate to Login page 2. Enter valid email & password 3. Click Login | Email: ks679485@gmail.com ¦ Pass: Test@123 | User logged in. Redirected to 'My Account' dashboard. | User logged in. Redirected to 'My Account' dashboard. | Pass | High
TC_LOG_002 | Login | Login Page | Verify login with invalid password | 1. Navigate to Login page 2. Enter valid email with wrong password 3. Click Login | Email: ks679485@gmail.com ¦ Pass: WrongPass | Error: 'Warning: No match for E-Mail Address and/or Password.' | validation error :- Warning: No match for E-Mail Address and/or Password. | Pass | High
TC_LOG_003 | Login | Login Page | Verify login with blank fields | 1. Navigate to Login page 2. Leave email & password blank 3. Click Login | Email: blank ¦ Pass: blank | Warning message displayed. Login does not proceed. | Warning: No match for E-Mail Address and/or Password login does not proceed | Pass | High
TC_LOG_004 | Login | Login Page | Verify Forgot Password link navigates correctly | 1. Navigate to Login page 2. Click 'Forgotten Password' link | N/A | User is redirected to Forgot Password page. | User is redirected to Forgot Password page. | Pass | Medium
TC_SRC_001 | Search | Search Bar | Verify search with a valid product name | 1. Enter 'iPhone' in search bar 2. Click Search icon | Keyword: iPhone | Search results page displays products matching 'iPhone'. | result page display product matching 'Iphone' | Pass | High
TC_SRC_002 | Search | Search Bar | Verify search with invalid/random keyword | 1. Enter 'xyzabc123' in search bar 2. Click Search icon | Keyword: xyzabc123 | Message: 'There is no product that matches the search criteria.' | message displayed:- There is no product that matches the search criteria | Pass | Medium
TC_SRC_003 | Search | Search Bar | Verify search with empty keyword | 1. Leave search bar empty 2. Click Search icon | Keyword: (blank) | Criteria message displayed or all products shown. | message displayed :- There is no product that matches the search criteria | Pass | Medium
TC_CRT_001 | Shopping Cart | Add to Cart | Verify adding a product to cart | 1. Search a product 2. Open product page 3. Click 'Add to Cart' | Product: MacBook | Success message: 'Success: You have added MacBook to your shopping cart!' | message Displayed:- Success: You have added MacBook to your shopping cart! | Pass | High
TC_CRT_002 | Shopping Cart | Cart | Verify updating product quantity in cart | 1. Open Cart 2. Change quantity to 2 3. Click Update | Qty: 2 | Cart updates. Total price reflects new quantity. | Cart updates. Total price reflects new quantity | Pass | High
TC_CRT_003 | Shopping Cart | Cart | Verify removing a product from cart | 1. Open Cart 2. Click Remove (X) for a product | N/A | Product removed. Cart shows updated list or 'Your shopping cart is empty!' | Success: You have modified your shopping cart! Product removed. Cart shows updated list or 'Your shopping cart is empty!' | Pass | High
TC_CRT_004 | Shopping Cart | Cart | Verify cart retains items after login | 1. Add product without login 2. Login 3. Check cart | N/A | Cart items retained after login (or merged). | Cart items retained after login (or merged). | Pass | Medium
TC_CHK_001 | Checkout | Checkout Process | Verify guest checkout navigation | 1. Add product to cart 2. Click Checkout 3. Select 'Guest Checkout' 4. Fill required details | Name, Address, Email filled | Checkout proceeds to payment step. | Checkout proceeds to payment step. | Pass | High
TC_CHK_002 | Checkout | Checkout Process | Verify checkout requires address details | 1. Add product 2. Click Checkout 3. Leave address blank 4. Click Continue | Address fields blank | Validation errors for mandatory address fields. | Your guest account information has been saved! | Fail | High
TC_WSH_001 | Wish List | Add to Wishlist | Verify adding product to wishlist (logged in) | 1. Login 2. Open product 3. Click 'Add to Wish List' | User logged in | Success: 'You have added [Product] to your wish list!' | Success: 'You have added [Product] to your wish list!' | Pass | Medium
TC_WSH_002 | Wish List | Add to Wishlist | Verify wishlist prompts login for guests | 1. Logout 2. Open product 3. Click 'Add to Wish List' | User not logged in | Redirected to Login page with message to login. | Redirected to Login page with message to login. | Pass | Medium
TC_ACC_001 | My Account | Edit Account | Verify updating account information | 1. Login 2. Go to My Account > Edit Account 3. Change First Name 4. Click Continue | New First Name: Jane | Success: 'Your account has been successfully updated!' | Success: 'Your account has been successfully updated!' | Pass | Medium
TC_ACC_002 | My Account | Change Password | Verify changing password with correct current password | 1. Login 2. Go to My Account > Change Password 3. Enter old & new password 4. Submit | Old: Test@123 ¦ New: NewPass@456 | Success: Password changed. Login works with new password. | Success: Your password has been successfully updated. Login works with new password. | Pass | High
TC_REV_001 | Product Review | Add Review | Verify submitting a product review | 1. Login 2. Open any product page 3. Click 'Write a Review' 4. Fill form 5. Click Submit | Name: John ¦ Review text: Good product ¦ Rating: 4 | Review submitted. 'Thank you for your review.' message shown. | review is not submitted because module review section its not working | Fail | Low
TC_NAV_001 | Navigation | Header | Verify all top navigation links work | 1. Click each menu item in the top navigation | N/A | Each link navigates to the correct page without error. | Navbar section like desktop, MP3 player , components and laptop or notebook component are not working | Fail | Medium
TC_NAV_002 | Navigation | Footer | Verify footer links are functional | 1. Scroll to footer 2. Click each link | N/A | All footer links navigate to correct pages. | All footer links navigate to correct pages. | Pass | Low

## RTM Report
REQUIREMENTS TRACEABILITY MATRIX (RTM) – OpenCart
Req. ID | Requirement Description | Module | Test Case IDs Mapped | No. of TC | Executed | Passed | Failed | Coverage Status
REQ_001 | User should be able to register a new account | User Registration | TC_REG_001, TC_REG_002, TC_REG_003, TC_REG_004, TC_REG_005 | 5 | 5 | 5 | 0 | Covered
REQ_002 | User should be able to login & logout | Login | TC_LOG_001, TC_LOG_002, TC_LOG_003, TC_LOG_004 | 4 | 4 | 4 | 0 | Covered
REQ_003 | User should be able to search for products | Search | TC_SRC_001, TC_SRC_002, TC_SRC_003 | 3 | 3 | 3 | 0 | Covered
REQ_004 | User should be able to add/remove items in cart | Shopping Cart | TC_CRT_001, TC_CRT_002, TC_CRT_003, TC_CRT_004 | 4 | 4 | 4 | 0 | Covered
REQ_005 | User should be able to complete checkout | Checkout | TC_CHK_001, TC_CHK_002 | 2 | 2 | 1 | 1 | 1 Failed
REQ_006 | User should be able to manage wish list | Wish List | TC_WSH_001, TC_WSH_002 | 2 | 2 | 2 | 0 | Covered
REQ_007 | User should be able to manage account info | My Account | TC_ACC_001, TC_ACC_002 | 2 | 2 | 2 | 0 | Covered
REQ_008 | User should be able to submit product reviews | Product Review | TC_REV_001 | 1 | 1 | 0 | 1 | 1 Failed
REQ_009 | Navigation links must work correctly | Navigation | TC_NAV_001, TC_NAV_002 | 2 | 2 | 1 | 1 | 1 Failed

## Bug Report
BUG REPORT – OpenCart Manual Testing Project
Bug ID | TC ID | Module | Bug Title | Description / Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Date Reported
BUG_001 | TC_CHK_002 | Checkout | Error message not show while address field blank | 1. Add product 2. Click Checkout 3. Leave address blank 4. Click Continue | Validation errors for mandatory address fields. | Your guest account information has been saved! | High | High | Open | Krishan Singh | 2026-05-28
BUG_002 | TC_REV_001 | Product Review | product review is not accepted by review section | 1. Login 2. Open any product page 3. Click 'Write a Review' 4. Fill form 5. Click Submit | Review submitted. 'Thank you for your review.' message shown. | review is not submitted because module review section its not working | Medium | Medium | Open | Krishan Singh | 2026-05-29
BUG_003 | TC_NAV_001 | Navigation | Navbar section like desktop, MP3 player , components and laptop or notebook component are not working | 1. Click each menu item in the top navigation | Each link navigates to the correct page without error. | some components are not working | Critical | High | Open | Krishan Singh | 2026-05-29

## Summary Report
TEST SUMMARY REPORT – OpenCart Manual Testing
Project | OpenCart E-Commerce Application
Version Tested | OpenCart 3.x (Demo)
Test Cycle | Cycle 1
Test Period | 25-05-2026 to 30-05-2026
Tester | Krishna Singh
Environment | Chrome ¦ Windows 10 ¦ demo.opencart.com
Overall Status | PASS WITH DEFECTS
TEST EXECUTION METRICS
Metric | Count | Metric | Count | Metric | Count
Total Test Cases | 25 | Passed | 22 | Pass % | 88%
Total Executed | 25 | Failed | 3 | Fail % | 12%
Not Executed | 0 | Blocked | 0 | Block% | 0%
DEFECT SUMMARY BY SEVERITY
Severity | Count
Critical (S1) | 1
High (S2) | 1
Medium (S3) | 1
Low (S1) | 0